## Instructions
Instructions | Enter your team name as specified in the cell below. When doing cross-team acceptance testing, enter the name for the testing group. Fill-in the Test Plan worksheet with all the remaining User Stories in your Product Backlog. Since Product acceptance is from the perspective of the end-user, only add User Stories that pertain to the Owner or Buyer and do not include User Stories specifically for the REST API service (e.g. AS a developer...). As your user stories are refined, add the acceptance criteria for each user story. Use a separate worksheet to provide any specific test case data that the tester needs to use. As tests are performed in each sprint, indicate Pass/Fail. Note that there are separate columns for each sprint. The tester should add initials and a date in the comments column. If the test failed, the tester is required to add additional information about the failure. The status cell will color code based on the test results. The comments cell will color code when a test result exists but no information is entered. Save this test plan with a name formatted as "term-swen-261-sec-letter name", e.g. 2171-swen-261-10-a Speedy Racers.xslx. Submit this file per the instructions specified for the sprint submissions and cross-team testing.
Team Name | 2211-swen-261-01-4D coolname
Testing Team Name | fill in when doing cross-team testing

## Test Plan
User Story | Acceptance Criterion | Sprint 2 | Tester initials; date; comments (required if test failed) | Sprint 3 | Tester initials; date; comments (required if test failed)
Log in as User | Given a textbox for username and password when I fill in my username and password then I expect to be logged in with the same saved data I left on logout.
Logout as User | Given a button to logout when click it then I expect to be logged out and all the changes I made to data saved in the database.
Log in as Admin | Given a textbox for username and password when I Iog in as admin then I expect to gain access to the inventory and admin privileges.
Logout as Admin | Given a button to logout when click it then I expect to be logged out and all the changes I made to data saved in the database.
Create accessory | Given A create disc inventory when I fill out the criteria and click create then I expect the new disc to be added to inventory.
Update Inventory | Given an admin UI with a tabular view of all items and their attributes when I update the quantities and click update then I expect the inventory to be updated.
Add Disc to Cart | Given A disc when I add it to my cart then the disc is placed in my cart and stored.
Remove Disc from Cart | Given A disc when I remove it from to my cart then the disc is removed from my cart and stored.
Change Disc Quantity | Given an accessory when I add to the quantity then I can buy 1 more of the same accessory.
Given an accessory when I subtract from the quantity then I can buy 1 less of the same accessory.
Given an accessory when I set the quantity then I can buy that number of the same accessory.
Proceed to Checkout | Given I am done shopping when I proceed to checkout then I expect to purchase the items in my cart.
Search Bar for Disc | Given I want to purchase a specific item when I search for that item then that item should appear.
Enhanced Shopping Cart | Given my cart is full of items when I select purchase cart then I expect to see my receipt. If there are any conflicts with items I am purchasing, the system asks if I want to proceed.
Given My cart is full of items when scroll down below the list then I expect to see my expected total and count.
Lessons Backend | Given Lesson Information (title, description, days offered, price, range of dates when offered) when I Submit the information then I EXPECT lesson to be created.
Purchase-now accessory | Given an item when I want to purchase it then I expect to purchase only that item.
Scheduling Sessions | Given I want to be mentored when I schedule a training session then I expect to be scheduled in the system.
UI consistency | Given any page on the Acadia site when observe it then I expect the same formatting and style across the board.
Filter list of accessories | Given I am searching for a specific item when I filter the options for it then I expect to be shown what I am searching for if it is available.
Disc Images | Given any page on the Acadia site that contains discs when I observe it then I expect to see what the disc looks like based on the color I select.
Coaching Discussion | Given I want to communicate with my coach when I message him then I expect to be able to send and receive messages from him.